## Sheet1
Week | <component> | difficulty
2022-01-03 | create git hub repo | easy | difficulty
2022-01-10 | launch azure cloud shell and generate ssh-keys | easy | Column1
2022-01-17 | create the makefile | medium | easy
2022-01-24 | create requirements.txt | medium | medium
2022-01-31 | create the python venv | easy | hard
2022-02-07 | create the script file | hard
2022-02-14 | create the test file | medium
2022-02-21 | test current code | easy
2022-02-28 | create a git actions workflow | medium
2022-03-07 | verify remote tests with git actions | easy
2022-03-14 | replace scaffold code with flask starter code | easy
2022-03-21 | create service in azure | hard
2022-03-28 | run service and check results | medium
2022-04-04 | enable azure pipeline | easy
2022-04-11 | deploy the project in azure pipeline | medium
2022-04-18 | create architectural diagram | wasy
2022-04-25 | update read me file | medium
2022-05-02 | prepare demo | hard
Goals
Q1 | define plan
Q1 | learn continuous integration with git actions
Q1 | define testing and linting stages
Q2 | setup Azure App service
Q2 | setup CD with azure pipeline
Q2 | setup Documentation
Q2 | setup Demo